## README
Item | Content
Purpose | Delivery blueprint for the Oostervelde invoice-check build (MCP server + Claude skill), 48-hour solo delivery.
How to use | Product Backlog = source of truth. PM Import = same data as the Jira CSV. Statuses reflect the real state at generation time.
Status legend | Draft → Ready → In Progress → Blocked → Code Review → QA Testing → UAT → Done
Priority legend | P0 critical path · P1 high · P2 medium · P3 nice-to-have (Jira: Highest/High/Medium/Low)
Waves | W1 Foundations & parsing · W2 Core rules · W3 Cross-invoice rules, MCP, run · W4 Skill live, verification, delivery
Workstreams | WS-A Data & parsing · WS-B Rule engine · WS-C MCP & skill · WS-D Verification & docs
Conventions | Branch feat/oic-<n>/<title> · Conventional Commits with (OIC-###) · see CLAUDE.md
Totals | 35 stories · 107 points · sprints (points): S1=25, S2=24, S3=32, S4=26

## Project Overview
Topic | Detail
Summary | Local MCP server + Claude skill that checks 40 Dutch contractor invoices (4 layouts) against Article 4 of the Woonkring Oostervelde framework contract and gives Sanne a review list; she decides everything.
Objectives | Correct to the cent · no false flags · evidence Sanne can forward unedited · explain every difference with her 10 verdicts · honest about gaps.
Target users | Sanne Verbeek, accounts payable (signs off every payment). Assessors at MSTR.
KPIs | All 40 invoices reviewed · golden table passes · differences with Sanne explained 10/10 · README runs in 10 min · video <= 5 min.
Constraints | 48 hours from receipt · solo · Dutch documents · money in cents · nothing may reach a contractor without Sanne.
Assumptions | See Gaps & Assumptions.
Top risks | Misreading Dutch contract rules · parser trusting a wrong layout · overconfident flags · skill not exercised live.

## Product Roadmap
Phase | Wave | Scope | Release target | Priority | Dependencies
MVP / Phase 1 | W1 | Foundations + 4 parsers | Hour 12 | P0 | -
MVP / Phase 1 | W2 | Core rules | Hour 24 | P0 | W1
MVP / Phase 1 | W3 | Cross-invoice rules, MCP server, first run | Hour 36 | P0 | W2
MVP / Phase 1 | W4 | Skill live, comparison, verification, NOTES, video, submit | Hour 48 | P0 | W3
Phase 2 (after MSTR call) | - | PDF/OCR input, ERP export, learning from overrides | TBD | P3 | MVP

## Epic Backlog
Epic ID | Name | Description | Business value | Priority | Wave | Dependencies | Acceptance criteria | Status
EP-01 | Foundations & dataset | Repo, Dutch number/date handling, dataset loaders, translated contract. | Everything downstream depends on correct Dutch parsing and a translated contract. | P0 | W1 | - | Contract Art. 4 translated; money/date helpers tested; dataset loads. | Done
EP-02 | Invoice parsing (4 layouts) | Normalise Hoekstra, De Wit, Bosman and Jansen invoices into one schema. | Without a clean schema no rule can be trusted. | P0 | W1 | EP-01 | All 40 invoices parse; every parsed invoice reconciles with its own stated totals unless the invoice itself is wrong. | Done
EP-03 | Contract rule engine | One deterministic rule per Article 4 clause; findings with article, line, amount, evidence. | Amounts must be correct to the cent; Sanne must be able to forward the reasoning unedited. | P0 | W2 | EP-02 | Golden table for all 40 invoices passes; no false flags on clean invoices. | Done
EP-04 | MCP server | Small, clearly named tools over the dataset and engine. | The skill needs tools, not prompts, for facts and maths. | P0 | W3 | EP-03 | 11 tools callable over stdio by a real MCP client. | Done
EP-05 | Skill & Sanne-in-the-loop | Skill that presents, asks Sanne, logs decisions and overrides; never sends. | Sanne signs off every payment; trust is the product. | P0 | W3 | EP-04 | Skill covers present → decide → log → draft → close; no send path exists. | In Progress
EP-06 | The run, comparison & drafts | Run all 40, total the dispute, compare with Sanne's 10, Dutch e-mail drafts. | The assignment's measurable output. | P1 | W3 | EP-03 | Review list, comparison and drafts regenerate with one command. | Done
EP-07 | Verification & submission | Independent check, NOTES.md, README, video, submit. | Explainability and honesty are scored. | P1 | W4 | EP-06 | NOTES.md has the four headings; README runs in 10 minutes; video recorded; mail sent. | In Progress

## Feature Backlog
Feature ID | Epic | Name | Description | Priority | Complexity | Dependencies | Status
F-01 | EP-01 | Dutch formats & loaders | Money, dates, CSV, contract translation | P0 | M | - | Done
F-02 | EP-02 | Supplier parsers | Four layouts to one schema + self-check | P0 | L | US-003 | Done
F-03 | EP-03 | Price & indexation | Execution-date pricing, unit conversion | P0 | L | US-003, US-004, US-009 | Done
F-04 | EP-03 | Work-order rules | Call-out fee, hours/MU, meerwerk/GA, unknown WO | P0 | L | US-004, US-010 | Done
F-05 | EP-03 | VAT rule | 9 % / 21 % by code and build year | P0 | M | US-010 | Done
F-06 | EP-03 | Cross-invoice rules | Duplicates and credit-note netting | P0 | M | US-011, US-012 | Done
F-07 | EP-03 | Arithmetic & verdict | Own-arithmetic checks, exact VAT, verdict logic | P0 | M | US-009, US-014, US-016 | Done
F-08 | EP-04 | MCP tools | Read tools, check, review_all, drafts, decision log | P0 | L | US-004, US-009, US-019 | Done
F-09 | EP-05 | Skill & HITL | Skill workflow and override loop | P0 | M | US-021, US-023 | In Progress
F-10 | EP-06 | Run & compare | Review list, comparison, Dutch drafts, golden tests | P1 | M | US-019 | Done
F-11 | EP-07 | Verification & delivery | Blind audit, NOTES, README, video, submit | P1 | M | US-026, US-028, US-030 | In Progress

## Product Backlog
Story ID | Epic | Feature | Summary | User story | Acceptance criteria | Priority | Points | Wave | Workstream | Sprint | Dependencies | Status
US-001 | EP-01 | F-01 | Translate Article 4 and build a glossary | As the builder I want the contract in English so I don't misread Dutch rules. | ☐ Every Art. 4.1-4.10 clause translated ☐ Glossary of invoice terms (spoed, meerwerk, voorrijkosten, ...) ☐ Dutch text kept verbatim for quoting | P0 | 3 | W1 | WS-A | S1 | - | Done
US-002 | EP-01 | F-01 | Scaffold TypeScript/vitest/tsx project | As the builder I want a runnable repo in minutes. | ☐ npm install && npm test works from clean checkout ☐ Strict TypeScript | P0 | 2 | W1 | WS-A | S1 | - | Done
US-003 | EP-01 | F-01 | Dutch money and date parsing | As the builder I want 1.234,56 and 02/01/2026 parsed correctly. | ☐ Money in integer cents, no floats ☐ DD/MM, DD-MM, ISO and '5 januari 2026' all parse; impossible dates rejected | P0 | 3 | W1 | WS-A | S1 | US-002 | Done
US-004 | EP-01 | F-01 | Load price list, work orders, contract text, Sanne's verdicts | As the engine I want typed reference data. | ☐ Quoted CSV fields handled ☐ DATA_DIR override works | P0 | 2 | W1 | WS-A | S1 | US-002 | Done
US-005 | EP-02 | F-02 | Hoekstra parser | As Sanne I want Hoekstra invoices read correctly, including credit notes. | ☐ Lines, units (incl. 'rol 25 m', 'post'), totals, VAT parsed ☐ Credit note links to original invoice | P0 | 3 | W1 | WS-A | S1 | US-003 | Done
US-006 | EP-02 | F-02 | Bosman parser | As Sanne I want Bosman invoices read correctly. | ☐ Pipe layout parsed ☐ ISO dates; meerwerk flagged | P0 | 2 | W1 | WS-A | S1 | US-003 | Done
US-007 | EP-02 | F-02 | Jansen parser (day-first dates) | As Sanne I want Jansen invoices read correctly. | ☐ Two-line item layout parsed ☐ 02/01/2026 = 2 January, not 1 February | P0 | 3 | W1 | WS-A | S1 | US-003 | Done
US-008 | EP-02 | F-02 | De Wit parser (letter style) | As Sanne I want De Wit's letter-style invoices read correctly. | ☐ Dutch month names ☐ VAT rate per line ☐ Meerwerk line containing an extra colon | P0 | 5 | W1 | WS-A | S1 | US-003 | Done
US-009 | EP-02 | F-02 | Parser self-check against stated totals | As the builder I want parser errors separated from invoice errors. | ☐ Lines sum, VAT and total checked per invoice ☐ Only 2026-0052 and DW26-016 have real arithmetic errors | P0 | 2 | W1 | WS-A | S1 | US-005, US-006, US-007, US-008 | Done
US-010 | EP-03 | F-03 | Price and indexation by execution date, with unit conversion | As Sanne I want prices checked at the right year's price. | ☐ Work executed before 2026-01-01 uses 2025 price; else +3.2 % rounded per unit ☐ rol 25 m vs m compared per list unit ☐ Invoice date never decides the price year | P0 | 5 | W2 | WS-B | S2 | US-003, US-004, US-009 | Done
US-011 | EP-03 | F-04 | Call-out fee rule (Art. 4.3) | As Sanne I want call-out fees only on spoed and once. | ☐ Regular work: whole fee disputed ☐ Spoed: second fee disputed | P0 | 3 | W2 | WS-B | S2 | US-010 | Done
US-012 | EP-03 | F-04 | Hours rule with MU approvals (Art. 4.4) | As Sanne I want hours above the maximum caught. | ☐ Max + approved MU hours ☐ Excess valued at contract rate | P0 | 3 | W2 | WS-B | S2 | US-010 | Done
US-013 | EP-03 | F-04 | Meerwerk rule with GA approvals (Art. 4.5) | As Sanne I want extra work handled exactly. | ☐ <= 250 free ☐ Above 250 without GA: nothing paid (not even 250) ☐ With GA: at most approved amount | P0 | 5 | W2 | WS-B | S2 | US-010 | Done
US-014 | EP-03 | F-05 | VAT 9 % / 21 % rule (Art. 4.6) | As Sanne I want VAT checked per line, not by counting VAT lines. | ☐ 9 % only for W01/W04 on homes older than two years ☐ Overcharged VAT disputed; undercharged VAT held for Sanne | P0 | 5 | W2 | WS-B | S2 | US-010 | Done
US-015 | EP-03 | F-04 | Off-list items, unknown work orders, supplier mismatch (Art. 4.7, 4.9) | As Sanne I want unknown orders on hold. | ☐ Unknown WO = hold, nothing else claimed ☐ Off-list item flagged as judgment | P0 | 3 | W2 | WS-B | S2 | US-004 | Done
US-016 | EP-03 | F-06 | Duplicates and credit-note netting (Art. 4.8) | As Sanne I want cross-invoice problems found. | ☐ Identical second invoice for a WO disputed in full ☐ Credit note netted; not disputed twice | P0 | 5 | W3 | WS-B | S3 | US-011, US-012 | Done
US-017 | EP-03 | F-07 | Invoice arithmetic checks | As Sanne I want the contractor's own sums verified. | ☐ Line = qty x price ☐ Total = subtotal + VAT ☐ Overstated totals shown in their own column | P0 | 3 | W3 | WS-B | S3 | US-009 | Done
US-018 | EP-03 | F-07 | Exact VAT reclaim per VAT bucket | As Sanne I want VAT correct to the cent. | ☐ Reclaim = billed VAT - VAT on accepted amounts per rate ☐ Per-finding VAT reconciles to invoice-level figure | P0 | 3 | W3 | WS-B | S3 | US-014 | Done
US-019 | EP-03 | F-07 | Verdict logic and needs-Sanne flag | As Sanne I want to see what is uncertain first. | ☐ approve / dispute / hold rules documented ☐ judgment findings flagged | P0 | 3 | W3 | WS-B | S3 | US-016, US-017, US-018 | Done
US-020 | EP-04 | F-08 | MCP server skeleton and read tools | As Claude I want tools for facts. | ☐ list_invoices, get_invoice, get_price, get_work_order, get_contract_rule ☐ Unknown WO returns an error mentioning Art. 4.9 | P0 | 3 | W3 | WS-C | S3 | US-004, US-009 | Done
US-021 | EP-04 | F-08 | check_invoice, find_duplicates, review_all | As Claude I want the engine behind tools. | ☐ Findings carry article, line, amount, evidence, Dutch sentence ☐ Errors are clean, not crashes | P0 | 3 | W3 | WS-C | S3 | US-019, US-020 | Done
US-022 | EP-04 | F-08 | draft_dispute_email (Dutch draft) | As Sanne I want the e-mail written for me. | ☐ Dutch; cites article and amount; 10-day and 30-day wording ☐ Marked CONCEPT; nothing is sent | P0 | 3 | W3 | WS-C | S3 | US-021 | Done
US-023 | EP-04 | F-08 | Decision log tools | As Sanne I want my decisions and overrides remembered. | ☐ Override requires her reason ☐ Log is append-only JSONL | P0 | 3 | W3 | WS-C | S3 | US-021 | Done
US-024 | EP-04 | F-08 | Server test with a real MCP client over stdio | As the builder I want proof the server works. | ☐ Tools list, get_price, check_invoice, decisions tested via SDK client | P0 | 3 | W3 | WS-C | S3 | US-023 | Done
US-025 | EP-05 | F-09 | Skill: present, decide, log, draft, close | As Sanne I want Claude to keep me in charge. | ☐ Judgment items first ☐ Never sends or contacts anyone ☐ Overrides logged with reason | P0 | 3 | W4 | WS-C | S4 | US-021, US-023 | Done
US-026 | EP-05 | F-09 | Run the skill live in Claude Code/Desktop as Sanne | As the builder I want to see it work end to end. | ☐ Skill triggers on a natural request ☐ All tools reachable ☐ One override logged | P0 | 3 | W4 | WS-C | S4 | US-025 | Ready
US-027 | EP-05 | F-09 | Override-to-rule-update proposal loop | As the team I want overrides to improve the rules. | ☐ Skill proposes a change; a person edits code ☐ No automatic rule changes | P2 | 2 | W4 | WS-C | S4 | US-025 | Draft
US-028 | EP-06 | F-10 | Run all 40 and write the review list | As Sanne I want one list with a total. | ☐ review-list.md/.csv/.json generated by one command ☐ Totals: approve/dispute/hold, excl./incl. VAT | P0 | 3 | W3 | WS-D | S3 | US-019 | Done
US-029 | EP-06 | F-10 | Comparison with Sanne's 10 | As the assessor I want every difference explained. | ☐ Table + commentary per invoice ☐ Contract-based, not assuming Sanne is right | P0 | 3 | W4 | WS-D | S4 | US-028 | Done
US-030 | EP-06 | F-10 | Golden-table regression tests | As the builder I want to know when a number changes. | ☐ All 40 invoices asserted ☐ Rule-level tests with hand-computed values | P0 | 3 | W4 | WS-D | S4 | US-028 | Done
US-031 | EP-07 | F-11 | Independent blind audit and reconcile | As the builder I want a second opinion that did not see my code. | ☐ Separate agent audits the 40 invoices blind ☐ Every difference resolved or documented | P0 | 3 | W4 | WS-D | S4 | US-030 | Done
US-032 | EP-07 | F-11 | NOTES.md (four headings) | As the assessor I want decisions, handover, changes and gaps. | ☐ Decisions and translations; Where Sanne decides; What changed; What isn't finished | P0 | 3 | W4 | WS-D | S4 | US-031 | Done
US-033 | EP-07 | F-11 | README runnable in 10 minutes | As the assessor I want to run it quickly. | ☐ npm install, npm test, npm run all documented with expected output | P0 | 2 | W4 | WS-D | S4 | US-028 | Done
US-034 | EP-07 | F-11 | Record the <=5-minute video | As the assessor I want to see it running. | ☐ Skill running; one hard case; one thing it still gets wrong | P0 | 3 | W4 | WS-D | S4 | US-026, US-032 | Ready
US-035 | EP-07 | F-11 | Submit to nigel@mstr.nl and jason@mstr.nl | As the builder I want to deliver within 48 hours. | ☐ Zip/GitHub link + video link in one mail | P0 | 1 | W4 | WS-D | S4 | US-034 | Draft

## Sprint Backlog
Sprint | Goal | Stories | Est. points | Dependencies (earlier sprints) | Deliverables
S1 | Foundations + all four parsers | US-001, US-002, US-003, US-004, US-005, US-006, US-007, US-008, US-009 | 25 | - | Working increment: Foundations + all four parsers
S2 | Core rules: price, call-out, hours, meerwerk, VAT, unknown WO | US-010, US-011, US-012, US-013, US-014, US-015 | 24 | US-003; US-004; US-009 | Working increment: Core rules: price, call-out, hours, meerwerk, VAT, unknown WO
S3 | Cross-invoice rules, exactness, MCP server, first full run | US-016, US-017, US-018, US-019, US-020, US-021, US-022, US-023, US-024, US-028 | 32 | US-004; US-009; US-011; US-012; US-014 | Working increment: Cross-invoice rules, exactness, MCP server, first full run
S4 | Skill live, comparison, verification, NOTES, video, submit | US-025, US-026, US-027, US-029, US-030, US-031, US-032, US-033, US-034, US-035 | 26 | US-021; US-023; US-028 | Working increment: Skill live, comparison, verification, NOTES, video, submit

## Technical Backlog
Area | Task | Notes
Infra | Node 22 + TypeScript strict + tsx + vitest | No build step needed to run
Data | Typed loaders for CSV/MD dataset; DATA_DIR override | No database
API | 11 MCP tools over stdio | See API Contracts
Backend | Engine: one block per contract article | Integer cents everywhere
Security | Read-only tools; decision log is the only write; no network; no mail integration | Human in the loop by construction
DevOps | npm scripts; .mcp.json; Claude Desktop config snippet | See README
Monitoring | Tool errors are explicit messages, not crashes | Parsers throw on unknown layout

## Architecture & Decisions
Topic | Decision | Why
Components | parsers → engine → render → (cli ¦ MCP server) → skill | Each step testable alone
Stack | TypeScript + MCP SDK + zod | Locked; no swaps without an ADR
Rules in code, not prompt | All contract maths in deterministic code | Cent-exact, testable, explainable
Execution date | Price year follows execution date (Art. 4.2) | Contract text; Sanne's shortcut is wrong
Verdicts | approve / dispute / hold + judgment flag | Matches the brief; uncertainty visible
VAT reclaim | Per VAT bucket at invoice level | How invoices round; matches a corrected invoice
HITL | Proposals only; decisions logged; overrides need reasons | Sanne signs off
AI integration | Claude presents, asks, logs, drafts; never computes | See skill

## Data Model
Entity | Fields | Relationships | Notes
PriceItem | code, supplier, description, unit, price2025Cents | - | From price-agreement-2025.csv
WorkOrder | wo, supplier, type, maxLaborHours, MU approval + hours, GA approval + amount, built | 1 WO : n Invoice | Export is the authority
Invoice | supplier, number, dates (ISO), executionDate, workOrder, isCredit, creditOf, totals | 1 : n InvoiceLine, VatLine | Normalised from 4 layouts
InvoiceLine | description, qtyMilli, unit, unitPriceCents, amountCents, vatRatePct?, code?, isMeerwerk | n : 1 Invoice | qty in thousandths
Finding | article, kind, severity, confidence, amounts (excl/VAT/other), reasons EN/NL, evidence, Dutch quote | n : 1 InvoiceReview | Evidence Sanne can forward
InvoiceReview | verdict, findings, billed, disputed, creditApplied, needsSanne | 1 : 1 Invoice
Decision | at, invoiceNo, proposed, final, override, reason | n : 1 Invoice | JSONL, append-only
Migrations / seed | None (no database)

## API Contracts
Tool | Request | Response | Auth | Status
list_invoices | {} | [{file, supplier, invoiceNo, dates, workOrder, total}] | local stdio | Done
get_invoice | {invoice} | normalised invoice (cents) | local stdio | Done
get_price | {code, execution_date} | applicable price, indexed? | local stdio | Done
get_work_order | {work_order} | work order or error (Art. 4.9) | local stdio | Done
get_contract_rule | {query?} | [{id, titleNl, textNl, textEn}] | local stdio | Done
check_invoice | {invoice} | verdict + findings + amounts + evidence + Dutch text | local stdio | Done
find_duplicates | {} | duplicates, repeats, credit notes | local stdio | Done
review_all | {format?} | markdown or json review list + totals | local stdio | Done
draft_dispute_email | {invoice} | Dutch draft text (never sent) | local stdio | Done
record_decision | {invoice, final_verdict, sanne_reason, final_dispute_excl_eur?} | logged decision (override flag) | local stdio | Done
list_decisions | {} | decisions + overrides | local stdio | Done

## QA & Testing
Feature | Unit | Integration | Edge cases | Regression
Dutch formats | money.test: parse/format/rounding/indexation of all 19 prices | - | 31-02, '5 smarch', 02/01 vs 01/02 | parsers.test
Parsers | per layout | all 40 parse; arithmetic sweep finds exactly 2 real errors | 'post' unit, meerwerk with extra colon, credit note | parsers.test
Rules | per article with hand-computed values | golden table for 40 invoices | spoed twice, MU hours, GA cap, 9 % on new build | engine.test (40 golden invoices + rule tests)
MCP server | - | real MCP client over stdio | unknown invoice, unknown WO, override without reason | server.test
Skill | - | live run (US-026, open) | Sanne overrides a proposal | manual
UAT | - | Sanne persona walk-through | - | -

## DevOps & Deploy
Topic | Detail
Repo | Single repo; trunk-based; branch feat/oic-<n>/<title>
CI | npm ci && npm run typecheck && npm test
Environments | Local only (stdio MCP server); DATA_DIR/OUTPUT_DIR/DECISIONS_FILE env vars
Logging | Tool errors returned as messages; decisions in output/decisions.jsonl
Backup / DR | Dataset is read-only; outputs regenerate with `npm run all`

## Risk Register
Risk | Impact | Probability | Mitigation | Owner
Contract misread (Dutch) | High | Medium | Quote Dutch verbatim, translate in NOTES, blind second audit | Builder
Overconfident false flag | High | Low | needsSanne flag for judgment; tests on clean invoices | Builder
Parser trusts wrong layout | High | Low | Self-check vs stated totals; throw on unknown layout | Builder
Skill not exercised live | Medium | Medium | US-026 before recording video | Builder
Ambiguity resolved differently by MSTR key | Medium | Medium | Documented per decision; amounts shown both ways where small | Builder
Missing received-date for 10-day deadline | Low | High | Counted from invoice date; stated in list | Builder

## Future Improvements
Area | Idea
Input | PDF/OCR invoices; unseen layouts via a learned parser with human confirmation
Integration | ERP/booking export of approved lines; mail integration with explicit per-message approval
Learning | Turn repeated Sanne overrides into proposed rule changes (human-reviewed)
Contract | Load full contract, not just Art. 4; Dutch public-holiday calendar for deadlines
Scale | Multi-month history for cumulative hours/meerwerk per work order

## PM Import
Issue ID | Issue Type | Summary | Description | Epic Name | Epic Link | Priority | Story Points | Status | Labels | Sprint | Wave | Workstream | Blocked By
EP-01 | Epic | Foundations & dataset | Repo, Dutch number/date handling, dataset loaders, translated contract. Business value: Everything downstream depends on correct Dutch parsing and a translated contract. Acceptance: Contract Art. 4 translated; money/date helpers tested; dataset loads. Wave W1 | Foundations & dataset |  | Highest |  | Done | wave-1 epic-ep-01 phase-mvp p0 |  | W1
EP-02 | Epic | Invoice parsing (4 layouts) | Normalise Hoekstra, De Wit, Bosman and Jansen invoices into one schema. Business value: Without a clean schema no rule can be trusted. Acceptance: All 40 invoices parse; every parsed invoice reconciles with its own stated totals unless the invoice itself is wrong. Wave W1 | Invoice parsing (4 layouts) |  | Highest |  | Done | wave-1 epic-ep-02 phase-mvp p0 |  | W1
EP-03 | Epic | Contract rule engine | One deterministic rule per Article 4 clause; findings with article, line, amount, evidence. Business value: Amounts must be correct to the cent; Sanne must be able to forward the reasoning unedited. Acceptance: Golden table for all 40 invoices passes; no false flags on clean invoices. Wave W2 | Contract rule engine |  | Highest |  | Done | wave-2 epic-ep-03 phase-mvp p0 |  | W2
EP-04 | Epic | MCP server | Small, clearly named tools over the dataset and engine. Business value: The skill needs tools, not prompts, for facts and maths. Acceptance: 11 tools callable over stdio by a real MCP client. Wave W3 | MCP server |  | Highest |  | Done | wave-3 epic-ep-04 phase-mvp p0 |  | W3
EP-05 | Epic | Skill & Sanne-in-the-loop | Skill that presents, asks Sanne, logs decisions and overrides; never sends. Business value: Sanne signs off every payment; trust is the product. Acceptance: Skill covers present → decide → log → draft → close; no send path exists. Wave W3 | Skill & Sanne-in-the-loop |  | Highest |  | In Progress | wave-3 epic-ep-05 phase-mvp p0 |  | W3
EP-06 | Epic | The run, comparison & drafts | Run all 40, total the dispute, compare with Sanne's 10, Dutch e-mail drafts. Business value: The assignment's measurable output. Acceptance: Review list, comparison and drafts regenerate with one command. Wave W3 | The run, comparison & drafts |  | High |  | Done | wave-3 epic-ep-06 phase-mvp p1 |  | W3
EP-07 | Epic | Verification & submission | Independent check, NOTES.md, README, video, submit. Business value: Explainability and honesty are scored. Acceptance: NOTES.md has the four headings; README runs in 10 minutes; video recorded; mail sent. Wave W4 | Verification & submission |  | High |  | In Progress | wave-4 epic-ep-07 phase-mvp p1 |  | W4
US-001 | Story | Translate Article 4 and build a glossary | As the builder I want the contract in English so I don't misread Dutch rules. Acceptance criteria: - [ ] Every Art. 4.1-4.10 clause translated - [ ] Glossary of invoice terms (spoed, meerwerk, voorrijkosten, ...) - [ ] Dutch text kept verbatim for quoting Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-01 · Feature F-01 · Wave W1 · WS-A · Sprint S1 |  | Foundations & dataset | Highest | 3 | Done | wave-1 ws-a sprint-1 epic-ep-01 phase-mvp p0 | S1 | W1 | WS-A
US-002 | Story | Scaffold TypeScript/vitest/tsx project | As the builder I want a runnable repo in minutes. Acceptance criteria: - [ ] npm install && npm test works from clean checkout - [ ] Strict TypeScript Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-01 · Feature F-01 · Wave W1 · WS-A · Sprint S1 |  | Foundations & dataset | Highest | 2 | Done | wave-1 ws-a sprint-1 epic-ep-01 phase-mvp p0 | S1 | W1 | WS-A
US-003 | Story | Dutch money and date parsing | As the builder I want 1.234,56 and 02/01/2026 parsed correctly. Acceptance criteria: - [ ] Money in integer cents, no floats - [ ] DD/MM, DD-MM, ISO and '5 januari 2026' all parse; impossible dates rejected Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-01 · Feature F-01 · Wave W1 · WS-A · Sprint S1 |  | Foundations & dataset | Highest | 3 | Done | wave-1 ws-a sprint-1 epic-ep-01 phase-mvp p0 | S1 | W1 | WS-A | US-002
US-004 | Story | Load price list, work orders, contract text, Sanne's verdicts | As the engine I want typed reference data. Acceptance criteria: - [ ] Quoted CSV fields handled - [ ] DATA_DIR override works Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-01 · Feature F-01 · Wave W1 · WS-A · Sprint S1 |  | Foundations & dataset | Highest | 2 | Done | wave-1 ws-a sprint-1 epic-ep-01 phase-mvp p0 | S1 | W1 | WS-A | US-002
US-005 | Story | Hoekstra parser | As Sanne I want Hoekstra invoices read correctly, including credit notes. Acceptance criteria: - [ ] Lines, units (incl. 'rol 25 m', 'post'), totals, VAT parsed - [ ] Credit note links to original invoice Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-02 · Feature F-02 · Wave W1 · WS-A · Sprint S1 |  | Invoice parsing (4 layouts) | Highest | 3 | Done | wave-1 ws-a sprint-1 epic-ep-02 phase-mvp p0 | S1 | W1 | WS-A | US-003
US-006 | Story | Bosman parser | As Sanne I want Bosman invoices read correctly. Acceptance criteria: - [ ] Pipe layout parsed - [ ] ISO dates; meerwerk flagged Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-02 · Feature F-02 · Wave W1 · WS-A · Sprint S1 |  | Invoice parsing (4 layouts) | Highest | 2 | Done | wave-1 ws-a sprint-1 epic-ep-02 phase-mvp p0 | S1 | W1 | WS-A | US-003
US-007 | Story | Jansen parser (day-first dates) | As Sanne I want Jansen invoices read correctly. Acceptance criteria: - [ ] Two-line item layout parsed - [ ] 02/01/2026 = 2 January, not 1 February Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-02 · Feature F-02 · Wave W1 · WS-A · Sprint S1 |  | Invoice parsing (4 layouts) | Highest | 3 | Done | wave-1 ws-a sprint-1 epic-ep-02 phase-mvp p0 | S1 | W1 | WS-A | US-003
US-008 | Story | De Wit parser (letter style) | As Sanne I want De Wit's letter-style invoices read correctly. Acceptance criteria: - [ ] Dutch month names - [ ] VAT rate per line - [ ] Meerwerk line containing an extra colon Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-02 · Feature F-02 · Wave W1 · WS-A · Sprint S1 |  | Invoice parsing (4 layouts) | Highest | 5 | Done | wave-1 ws-a sprint-1 epic-ep-02 phase-mvp p0 | S1 | W1 | WS-A | US-003
US-009 | Story | Parser self-check against stated totals | As the builder I want parser errors separated from invoice errors. Acceptance criteria: - [ ] Lines sum, VAT and total checked per invoice - [ ] Only 2026-0052 and DW26-016 have real arithmetic errors Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-02 · Feature F-02 · Wave W1 · WS-A · Sprint S1 |  | Invoice parsing (4 layouts) | Highest | 2 | Done | wave-1 ws-a sprint-1 epic-ep-02 phase-mvp p0 | S1 | W1 | WS-A | US-005, US-006, US-007, US-008
US-010 | Story | Price and indexation by execution date, with unit conversion | As Sanne I want prices checked at the right year's price. Acceptance criteria: - [ ] Work executed before 2026-01-01 uses 2025 price; else +3.2 % rounded per unit - [ ] rol 25 m vs m compared per list unit - [ ] Invoice date never decides the price year Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-03 · Wave W2 · WS-B · Sprint S2 |  | Contract rule engine | Highest | 5 | Done | wave-2 ws-b sprint-2 epic-ep-03 phase-mvp p0 | S2 | W2 | WS-B | US-003, US-004, US-009
US-011 | Story | Call-out fee rule (Art. 4.3) | As Sanne I want call-out fees only on spoed and once. Acceptance criteria: - [ ] Regular work: whole fee disputed - [ ] Spoed: second fee disputed Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-04 · Wave W2 · WS-B · Sprint S2 |  | Contract rule engine | Highest | 3 | Done | wave-2 ws-b sprint-2 epic-ep-03 phase-mvp p0 | S2 | W2 | WS-B | US-010
US-012 | Story | Hours rule with MU approvals (Art. 4.4) | As Sanne I want hours above the maximum caught. Acceptance criteria: - [ ] Max + approved MU hours - [ ] Excess valued at contract rate Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-04 · Wave W2 · WS-B · Sprint S2 |  | Contract rule engine | Highest | 3 | Done | wave-2 ws-b sprint-2 epic-ep-03 phase-mvp p0 | S2 | W2 | WS-B | US-010
US-013 | Story | Meerwerk rule with GA approvals (Art. 4.5) | As Sanne I want extra work handled exactly. Acceptance criteria: - [ ] <= 250 free - [ ] Above 250 without GA: nothing paid (not even 250) - [ ] With GA: at most approved amount Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-04 · Wave W2 · WS-B · Sprint S2 |  | Contract rule engine | Highest | 5 | Done | wave-2 ws-b sprint-2 epic-ep-03 phase-mvp p0 | S2 | W2 | WS-B | US-010
US-014 | Story | VAT 9 % / 21 % rule (Art. 4.6) | As Sanne I want VAT checked per line, not by counting VAT lines. Acceptance criteria: - [ ] 9 % only for W01/W04 on homes older than two years - [ ] Overcharged VAT disputed; undercharged VAT held for Sanne Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-05 · Wave W2 · WS-B · Sprint S2 |  | Contract rule engine | Highest | 5 | Done | wave-2 ws-b sprint-2 epic-ep-03 phase-mvp p0 | S2 | W2 | WS-B | US-010
US-015 | Story | Off-list items, unknown work orders, supplier mismatch (Art. 4.7, 4.9) | As Sanne I want unknown orders on hold. Acceptance criteria: - [ ] Unknown WO = hold, nothing else claimed - [ ] Off-list item flagged as judgment Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-04 · Wave W2 · WS-B · Sprint S2 |  | Contract rule engine | Highest | 3 | Done | wave-2 ws-b sprint-2 epic-ep-03 phase-mvp p0 | S2 | W2 | WS-B | US-004
US-016 | Story | Duplicates and credit-note netting (Art. 4.8) | As Sanne I want cross-invoice problems found. Acceptance criteria: - [ ] Identical second invoice for a WO disputed in full - [ ] Credit note netted; not disputed twice Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-06 · Wave W3 · WS-B · Sprint S3 |  | Contract rule engine | Highest | 5 | Done | wave-3 ws-b sprint-3 epic-ep-03 phase-mvp p0 | S3 | W3 | WS-B | US-011, US-012
US-017 | Story | Invoice arithmetic checks | As Sanne I want the contractor's own sums verified. Acceptance criteria: - [ ] Line = qty x price - [ ] Total = subtotal + VAT - [ ] Overstated totals shown in their own column Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-07 · Wave W3 · WS-B · Sprint S3 |  | Contract rule engine | Highest | 3 | Done | wave-3 ws-b sprint-3 epic-ep-03 phase-mvp p0 | S3 | W3 | WS-B | US-009
US-018 | Story | Exact VAT reclaim per VAT bucket | As Sanne I want VAT correct to the cent. Acceptance criteria: - [ ] Reclaim = billed VAT - VAT on accepted amounts per rate - [ ] Per-finding VAT reconciles to invoice-level figure Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-07 · Wave W3 · WS-B · Sprint S3 |  | Contract rule engine | Highest | 3 | Done | wave-3 ws-b sprint-3 epic-ep-03 phase-mvp p0 | S3 | W3 | WS-B | US-014
US-019 | Story | Verdict logic and needs-Sanne flag | As Sanne I want to see what is uncertain first. Acceptance criteria: - [ ] approve / dispute / hold rules documented - [ ] judgment findings flagged Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-03 · Feature F-07 · Wave W3 · WS-B · Sprint S3 |  | Contract rule engine | Highest | 3 | Done | wave-3 ws-b sprint-3 epic-ep-03 phase-mvp p0 | S3 | W3 | WS-B | US-016, US-017, US-018
US-020 | Story | MCP server skeleton and read tools | As Claude I want tools for facts. Acceptance criteria: - [ ] list_invoices, get_invoice, get_price, get_work_order, get_contract_rule - [ ] Unknown WO returns an error mentioning Art. 4.9 Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-04 · Feature F-08 · Wave W3 · WS-C · Sprint S3 |  | MCP server | Highest | 3 | Done | wave-3 ws-c sprint-3 epic-ep-04 phase-mvp p0 | S3 | W3 | WS-C | US-004, US-009
US-021 | Story | check_invoice, find_duplicates, review_all | As Claude I want the engine behind tools. Acceptance criteria: - [ ] Findings carry article, line, amount, evidence, Dutch sentence - [ ] Errors are clean, not crashes Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-04 · Feature F-08 · Wave W3 · WS-C · Sprint S3 |  | MCP server | Highest | 3 | Done | wave-3 ws-c sprint-3 epic-ep-04 phase-mvp p0 | S3 | W3 | WS-C | US-019, US-020
US-022 | Story | draft_dispute_email (Dutch draft) | As Sanne I want the e-mail written for me. Acceptance criteria: - [ ] Dutch; cites article and amount; 10-day and 30-day wording - [ ] Marked CONCEPT; nothing is sent Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-04 · Feature F-08 · Wave W3 · WS-C · Sprint S3 |  | MCP server | Highest | 3 | Done | wave-3 ws-c sprint-3 epic-ep-04 phase-mvp p0 | S3 | W3 | WS-C | US-021
US-023 | Story | Decision log tools | As Sanne I want my decisions and overrides remembered. Acceptance criteria: - [ ] Override requires her reason - [ ] Log is append-only JSONL Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-04 · Feature F-08 · Wave W3 · WS-C · Sprint S3 |  | MCP server | Highest | 3 | Done | wave-3 ws-c sprint-3 epic-ep-04 phase-mvp p0 | S3 | W3 | WS-C | US-021
US-024 | Story | Server test with a real MCP client over stdio | As the builder I want proof the server works. Acceptance criteria: - [ ] Tools list, get_price, check_invoice, decisions tested via SDK client Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-04 · Feature F-08 · Wave W3 · WS-C · Sprint S3 |  | MCP server | Highest | 3 | Done | wave-3 ws-c sprint-3 epic-ep-04 phase-mvp p0 | S3 | W3 | WS-C | US-023
US-025 | Story | Skill: present, decide, log, draft, close | As Sanne I want Claude to keep me in charge. Acceptance criteria: - [ ] Judgment items first - [ ] Never sends or contacts anyone - [ ] Overrides logged with reason Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-05 · Feature F-09 · Wave W4 · WS-C · Sprint S4 |  | Skill & Sanne-in-the-loop | Highest | 3 | Done | wave-4 ws-c sprint-4 epic-ep-05 phase-mvp p0 | S4 | W4 | WS-C | US-021, US-023
US-026 | Story | Run the skill live in Claude Code/Desktop as Sanne | As the builder I want to see it work end to end. Acceptance criteria: - [ ] Skill triggers on a natural request - [ ] All tools reachable - [ ] One override logged Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-05 · Feature F-09 · Wave W4 · WS-C · Sprint S4 |  | Skill & Sanne-in-the-loop | Highest | 3 | Ready | wave-4 ws-c sprint-4 epic-ep-05 phase-mvp p0 | S4 | W4 | WS-C | US-025
US-027 | Story | Override-to-rule-update proposal loop | As the team I want overrides to improve the rules. Acceptance criteria: - [ ] Skill proposes a change; a person edits code - [ ] No automatic rule changes Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-05 · Feature F-09 · Wave W4 · WS-C · Sprint S4 |  | Skill & Sanne-in-the-loop | Medium | 2 | Draft | wave-4 ws-c sprint-4 epic-ep-05 phase-mvp p2 | S4 | W4 | WS-C | US-025
US-028 | Story | Run all 40 and write the review list | As Sanne I want one list with a total. Acceptance criteria: - [ ] review-list.md/.csv/.json generated by one command - [ ] Totals: approve/dispute/hold, excl./incl. VAT Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-06 · Feature F-10 · Wave W3 · WS-D · Sprint S3 |  | The run, comparison & drafts | Highest | 3 | Done | wave-3 ws-d sprint-3 epic-ep-06 phase-mvp p0 | S3 | W3 | WS-D | US-019
US-029 | Story | Comparison with Sanne's 10 | As the assessor I want every difference explained. Acceptance criteria: - [ ] Table + commentary per invoice - [ ] Contract-based, not assuming Sanne is right Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-06 · Feature F-10 · Wave W4 · WS-D · Sprint S4 |  | The run, comparison & drafts | Highest | 3 | Done | wave-4 ws-d sprint-4 epic-ep-06 phase-mvp p0 | S4 | W4 | WS-D | US-028
US-030 | Story | Golden-table regression tests | As the builder I want to know when a number changes. Acceptance criteria: - [ ] All 40 invoices asserted - [ ] Rule-level tests with hand-computed values Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-06 · Feature F-10 · Wave W4 · WS-D · Sprint S4 |  | The run, comparison & drafts | Highest | 3 | Done | wave-4 ws-d sprint-4 epic-ep-06 phase-mvp p0 | S4 | W4 | WS-D | US-028
US-031 | Story | Independent blind audit and reconcile | As the builder I want a second opinion that did not see my code. Acceptance criteria: - [ ] Separate agent audits the 40 invoices blind - [ ] Every difference resolved or documented Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-07 · Feature F-11 · Wave W4 · WS-D · Sprint S4 |  | Verification & submission | Highest | 3 | Done | wave-4 ws-d sprint-4 epic-ep-07 phase-mvp p0 | S4 | W4 | WS-D | US-030
US-032 | Story | NOTES.md (four headings) | As the assessor I want decisions, handover, changes and gaps. Acceptance criteria: - [ ] Decisions and translations; Where Sanne decides; What changed; What isn't finished Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-07 · Feature F-11 · Wave W4 · WS-D · Sprint S4 |  | Verification & submission | Highest | 3 | Done | wave-4 ws-d sprint-4 epic-ep-07 phase-mvp p0 | S4 | W4 | WS-D | US-031
US-033 | Story | README runnable in 10 minutes | As the assessor I want to run it quickly. Acceptance criteria: - [ ] npm install, npm test, npm run all documented with expected output Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-07 · Feature F-11 · Wave W4 · WS-D · Sprint S4 |  | Verification & submission | Highest | 2 | Done | wave-4 ws-d sprint-4 epic-ep-07 phase-mvp p0 | S4 | W4 | WS-D | US-028
US-034 | Story | Record the <=5-minute video | As the assessor I want to see it running. Acceptance criteria: - [ ] Skill running; one hard case; one thing it still gets wrong Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-07 · Feature F-11 · Wave W4 · WS-D · Sprint S4 |  | Verification & submission | Highest | 3 | Ready | wave-4 ws-d sprint-4 epic-ep-07 phase-mvp p0 | S4 | W4 | WS-D | US-026, US-032
US-035 | Story | Submit to nigel@mstr.nl and jason@mstr.nl | As the builder I want to deliver within 48 hours. Acceptance criteria: - [ ] Zip/GitHub link + video link in one mail Done gates: tests green, no regressions, reviewed PR, docs updated. Mapping: Epic EP-07 · Feature F-11 · Wave W4 · WS-D · Sprint S4 |  | Verification & submission | Highest | 1 | Draft | wave-4 ws-d sprint-4 epic-ep-07 phase-mvp p0 | S4 | W4 | WS-D | US-034

## Agile & AI Practices
Topic | Practice
Definition of Ready | AC testable · prerequisites done · <= 8 pts · design/contract linked · human-in-the-loop implications noted
Definition of Done | AC met · reviewed PR · npm test green · golden table updated with a reason if numbers change · NOTES.md updated if a decision changed · no float money
Ceremonies | Solo: 4 timeboxes (~12 h), demo at the end of each (green tests + regenerated review list)
AI-assisted dev | Claude builds from the translated contract; every rule needs a hand-computed test
AI-assisted test | Independent blind audit by a separate agent that never sees the code; differences reconciled
AI-assisted review | Findings must cite the article and quote the Dutch text; no claim without a tool result
AI in the product | Claude presents, asks and logs; code decides numbers; Sanne decides outcomes

## Gaps & Assumptions
# | Gap / assumption | Impact | Recommendation / what we did
1 | Date invoice was RECEIVED is not in the data (10-working-day deadline, 30-day payment) | Low | Count from invoice date; say so in the list. Ask MSTR/Sanne for the received date.
2 | Unit conversion rounding (167,70 / 25 = 6,708 per m) | Low (8 cents on h-2026-0057) | Compare exactly (no intermediate rounding): 21,68. If rounded to 6,71: 21,60. Ask MSTR.
3 | Contractor UNDER-charges VAT (9 % on new build / non-painting) | Medium | No money to reclaim; the invoice is wrong → HOLD for corrected invoice. Ask MSTR whether they expect dispute.
4 | Off-list item (Vogelwering): prior approval may exist outside the work-order export | Medium | Dispute, flagged judgment: Sanne confirms.
5 | 'Older than two years' uses build year vs execution year (> 2) | Low | Data has only 1968-1972 and 2025; no border case.
6 | Hours/meerwerk are aggregated per work order only across invoices in this batch | Low | Earlier months not available.
7 | No holiday calendar for working days | Low | Mon-Fri only.
8 | The skill was not yet run live in Claude by the time of generation | Medium | US-026 before the video.